## Original Estimate
[11 empty] | FIXED |  |  | HOURLY |  |  | Totals:
[6 empty] | Design Hours: |  | 0 | to | 0 | 0 | to | 0 | 0 | to | 0 | Min: | 178080
|  | Design hours fee |  | 125 |  | Dev Hours: |  | 1045.2 | to | 1327.2 | 162006 | to | 205716 | 130650 | to | 165900 | Max: | 221790
|  | Dev hours fee |  | 155 |  | QA Hours: |  |  |  | 169.2 | 16074 |  | 16074 | 16074 |  | 16074
|  | QA hours fee |  | 95 | [8 empty] | 221790 |  |  | 181974
|  | Ego Factor |  | 1.2
| Design hours min | Design Hours Max | Dev hours min | Dev hours max | QA hours estimate |  | UI or feature name
JD's Babbitt Bearings Solutions Web Portal
Employee portal
|  |  | 24 | 30 | 8 |  | Vacation, including calendar display and vacation request form
i |  |  | 8 | 12 | 4 |  | Vacation Report
i |  |  | 8 | 12 | 4 |  | Employee Management
i |  |  | 10 | 12 | 4 |  | Employee Document manager
i |  |  | 12 | 16 | 6 |  | Timesheets
i |  |  | 8 | 12 | 2 |  | Timesheet Report
i |  |  | 8 | 12 | 2 |  | Billing Report
|  |  | 12 | 16 | 2 |  | Skills
|  |  | 12 | 16 | 2 |  | Certificates & Certificate Edit
|  |  | 4 | 8 | 1 |  | Login
|  |  | 1 | 2 | 0 |  | Landing
|  |  | 8 | 12 | 2 |  | PIN Sign-off for vacation
|  |  | 10 | 12 | 2 |  | Job - Tablet screen
|  |  | 8 | 12 | 2 |  | Job Details
|  |  | 4 | 8 | 2 |  | Job History
|  |  | 8 | 12 | 2 |  | Add Part sub-screens for ID and OD
|  |  | 24 | 36 | 6 |  | Job - TV screen + controllers
Customer
|  |  | 4 | 6 | 1 |  | Add / Edit Customer
|  |  | 4 | 6 | 1 |  | Add / Edit Contact
Infrastructure
|  |  | 30 | 40 |  |  | On-site DB simulated in Azure
|  |  | 16 | 24 |  |  | SignalR for push notifications
Deployment and update
|  |  | 42 | 42 |  |  | Public web site - previously estimated at $6500 or 42 hours at current rate
|  |  | (inc) | (inc) |  |  | static pages - $2500
|  |  | (inc) | (inc) |  |  | pro photographer - $500
|  |  | (inc) | (inc) |  |  | customer job status portal
Common workflow screens - used with multiple Parts
|  |  | 24 | 32 | 3 |  | Photo management: store, upload, take photos
|  |  | 12 | 24 | 3 |  | Drawing / File management
|  |  | 8 | 12 | 1 |  | Final sign-off
|  |  | 8 | 12 | 1 |  | Sign-off pop-up for Workflow
|  |  | 4 | 8 | 1 |  | Delivery screen
|  |  | 8 | 12 | 1 |  | Part details info pop-up
|  |  | 16 | 24 | 2 |  | Custom drop-down control with "add new" for applicable fields
Workflows
|  |  | 80 | 80 | 12 |  | Babbitt Bearing - Motor - 14 screens
|  |  | 50 | 60 | 8 |  | Thrust Shoe - 5 screens
|  |  | 50 | 60 | 8 |  | Tapered Land Thrust Shoe - 6 screens
|  |  | 50 | 60 | 8 |  | Oil Deflector - 6 screens
|  |  | 50 | 60 | 8 |  | Oil Seal - 10 screens
|  |  | 50 | 60 | 8 |  | Hydrogen Seal - 10 screens
|  |  | 50 | 60 | 8 |  | Slinger Ring - 7 screens
|  |  | 50 | 60 | 8 |  | Thrust Plates - 5 screens
|  |  | 50 | 60 | 8 |  | Manufacturing New
Infrastructure
|  |  | 30 | 40 |  |  | On-site DB
|  |  | 8 | 12 |  |  | Azure DB
|  |  | 8 | 12 |  |  | Push between DBs

## EP Estimate
[10 empty] | FIXED |  |  | HOURLY |  |  | Totals:
[5 empty] | Design Hours: |  | 0 | to | 0 | 0 | to | 0 | 0 | to | 0 | Min: | 30590.1
| Design hours fee |  | 125 |  | Dev Hours: |  | 170.97 | to | 233.7 | 26500.35 | to | 36223.5 | 21371.25 | to | 29212.5 | Max: | 40313.25
| Dev hours fee |  | 155 |  | QA Hours: |  |  |  | 43.05 | 4089.75 |  | 4089.75 | 4089.75 |  | 4089.75
| QA hours fee |  | 95 | [8 empty] | 40313.25 | 25461 |  | 33302.25
| Ego Factor |  | 1.23
Design hours min | Design Hours Max | Dev hours min | Dev hours max | QA hours estimate |  | UI or feature name
JD's Babbitt Bearings Solutions Web Portal
Employee portal
|  | 26 | 32 | 8 |  | Vacation, including calendar display and vacation request form
|  | 8 | 12 | 4 |  | Vacation Report
|  | 8 | 12 | 4 |  | Employee Management
|  | 10 | 12 | 4 |  | Employee Document manager
|  | 12 | 16 | 6 |  | Timesheets
|  | 8 | 12 | 2 |  | Timesheet Report
|  | 0 | 0 | 0 |  | Billing Report (not done this milestone; estimated 8-12 hours)
|  | 12 | 16 | 2 |  | Skills
|  | 12 | 16 | 2 |  | Certificates & Certificate Edit
|  | 4 | 8 | 1 |  | Login
|  | 1 | 2 | 0 |  | Landing
Common
|  | 8 | 12 | 2 |  | PIN Sign-off for vacation
Infrastructure
|  | 30 | 40 |  |  | On-site DB simulated in Azure

## BB Estimate
[10 empty] | FIXED |  |  |  | HOURLY |  |  | Totals:
[5 empty] | Design Hours: |  | 0 | to | 0 | 0 | to | 0 |  | 0 | to | 0 | Min: | 39343.75
| Design hours fee |  | 108 |  | Dev Hours: |  | 226.25 | to | 357.5 | 35068.75 | to | 55412.5 |  | 24435 | to | 38610 | Max: | 59687.5
| Dev hours fee |  | 155 |  | QA Hours: |  |  |  | 45 | 4275 |  | 4275 |  | 4275 |  | 4275
| QA hours fee |  | 95 | [8 empty] | 59687.5 |  | 28710 |  | 42885
| Ego Factor |  | 1.25
Design hours min | Design Hours Max | Dev hours min | Dev hours max | QA hours estimate |  | UI or feature name
JD's Babbitt Bearings Solutions Web Portal
|  | 10 | 12 | 2 |  | Job - Tablet screen
|  | 8 | 12 | 2 |  | Job Details
|  | 4 | 8 | 2 |  | Job History
|  | 8 | 12 | 2 |  | Add Part sub-screens for ID and OD
|  | 12 | 14 | 1 |  | Job - TV screen
Customer
|  | 4 | 6 | 1 |  | Add / Edit Customer
|  | 4 | 6 | 1 |  | Add / Edit Contact
[6 empty] | Common workflow screens - used with multiple Parts | [5 empty] | Notes:
|  | 24 | 32 | 3 |  | Photo management: store, upload, take photos | [5 empty] | 24025 | Fixed cost of max estimate
|  | 12 | 24 | 3 |  | Drawing / File management
|  | 8 | 12 | 1 |  | Final sign-off
|  | 8 | 12 | 1 |  | Sign-off pop-up for Workflow
|  | 4 | 8 | 1 |  | Delivery screen
|  | 8 | 12 | 1 |  | Part details info pop-up
|  | 16 | 24 | 2 |  | Custom drop-down control with "add new" for applicable fields
Employee portal
|  | 8 | 12 | 1 |  | Billing Report (not done in previous milestone)
[6 empty] | Babbitt Bearing - Motor type - Workflow | [5 empty] | Notes:
|  | 8 | 12 | 1 |  | Incoming Inspection | [5 empty] | 15500 | Fixed Cost of max estimate
|  | 4 | 6 | 1 |  | Pre-cast Roughout
|  | 3 | 6 | 1 |  | Spincast Process
|  | 3 | 6 | 1 |  | Post-cast Clean up
|  | 3 | 6 | 1 |  | Post-cast Roughout
|  | 3 | 6 | 1 |  | Insulation Process
|  | 3 | 6 | 1 |  | Clean up Process
|  | 3 | 6 | 1 |  | Machining Inspetion
|  | 3 | 6 | 1 |  | Finish Bore Process
|  | 3 | 6 | 1 |  | Final Assembly
|  | 3 | 6 | 1 |  | Final Inspection
|  | 2 | 4 | 1 |  | Outgoing Dimensions form
|  | 2 | 4 |  |  | Conditional workflow navigation logic

## Sheet1
Vacation Date | Approved By | Hours
2015-06-03 | n/a | 4
2015-06-04 | n/a | 8
2015-07-05 | John | 8
Employee |  | Sun 8/1 | Mon 8/2 | Tue 8/3 | Wed 8/4 | Thu 8/5 | Fri 8/6 | Sat 8/7 | Sun 8/8 | Mon 8/9 | Tue 8/10 | Wed 8/11 | Thu 8/12 | Fri 8/13 | Sat 8/14 | Sat 8/15 | Total | ST | OT | DT
Jones, Timothy | Start | 6:01am | 6:00am | 6:15am | 5:58am | 6:00am | 6:00am | 6:00am | 6:01am | 6:00am | 6:15am | 5:58am | 6:00am | 6:00am | 6:00am | 6:00am
| End | 2:45pm | 2:30pm | 6:00pm | 8:15pm | 11:44pm | 3:00pm | 2:56pm | 2:45pm | 2:30pm | 6:00pm | 8:15pm | 11:44pm | 3:00pm | 2:56pm | 2:56pm
Skip meal | bar: 8 Sun 8/1 to 8 Sat 8/15
| Hours worked | 8.5 | 8.75 | 11.75 | 14.25 | 17.75 | 9 | 8.5 | 8.5 | 8.75 | 11.75 | 14.25 | 17.75 | 9 | 8.5 | 8.5 | 78.5 | 40 | 30 | 8.5
Flores, Alex | Start | 6:01am | 6:00am | 6:15am | 5:58am | 6:00am | 6:00am | 6:00am | 6:01am | 6:00am | 6:15am | 5:58am | 6:00am | 6:00am | 6:00am | 6:00am
| End | 2:45pm | 2:30pm | 6:00pm | 8:15pm | 11:44pm | 3:00pm | 2:56pm | 2:45pm | 2:30pm | 6:00pm | 8:15pm | 11:44pm | 3:00pm | 2:56pm | 2:56pm
Skip meal | bar: 8 Sun 8/1 to 8 Sat 8/15
| Hours worked | 8.5 | 8.75 | 11.75 | 14.25 | 17.75 | 9 | 8.5 | 8.5 | 8.75 | 11.75 | 14.25 | 17.75 | 9 | 8.5 | 8.5 | 78.5 | 40 | 30 | 8.5
White, Dillon | Start | 6:01am | 6:00am | 6:15am | 5:58am | 6:00am | 6:00am | 6:00am | 6:01am | 6:00am | 6:15am | 5:58am | 6:00am | 6:00am | 6:00am | 6:00am
| End | 2:45pm | 2:30pm | 6:00pm | 8:15pm | 11:44pm | 3:00pm | 2:56pm | 2:45pm | 2:30pm | 6:00pm | 8:15pm | 11:44pm | 3:00pm | 2:56pm | 2:56pm
Skip meal | bar: 8 Sun 8/1 to 8 Sat 8/15
| Hours worked | 8.5 | 8.75 | 11.75 | 14.25 | 17.75 | 9 | 8.5 | 8.5 | 8.75 | 11.75 | 14.25 | 17.75 | 9 | 8.5 | 8.5 | 78.5 | 40 | 30 | 8.5
Washington, Abraham | Start | 6:01am | 6:00am | 6:15am | 5:58am | 6:00am | 6:00am | 6:00am | 6:01am | 6:00am | 6:15am | 5:58am | 6:00am | 6:00am | 6:00am | 6:00am
| End | 2:45pm | 2:30pm | 6:00pm | 8:15pm | 11:44pm | 3:00pm | 2:56pm | 2:45pm | 2:30pm | 6:00pm | 8:15pm | 11:44pm | 3:00pm | 2:56pm | 2:56pm
Skip meal | bar: 8 Sun 8/1 to 8 Sat 8/15
| Hours worked | 8.5 | 8.75 | 11.75 | 14.25 | 17.75 | 9 | 8.5 | 8.5 | 8.75 | 11.75 | 14.25 | 17.75 | 9 | 8.5 | 8.5 | 78.5 | 40 | 30 | 8.5
[7 empty] | Total | ST | OT | DT
[7 empty] | 0 | 40 | 30 | 8.5
[7 empty] | 0 | 40 | 30 | 8.5
[7 empty] | 0 | 40 | 30 | 8.5
[7 empty] | 0 | 40 | 30 | 8.5

## Sheet2
3.5324 | 3.5445 | 3.5343